## v1
|  | Semester 1 | [11 empty] | Semester 2
| 1 Hour per column | Sprint 8 (11/14/2022 - 11/20/2022) - Capacity: 48 hrs |  | Sprint 9 (11/21/2022 - 11/27/2022) - Capacity: 18 hrs |  |  | Sprint 10 (11/28/2022 - 12/4/2022) - Capacity: 32 |  |  | Sprint 11 (12/5/2022 - 12/11/2022) - Capacity: 16 |  |  |  | Sprint 12 (1/23/2023 - 1/29/2023) - Capacity: 48 |  | Sprint 13 (1/30/2023 - 2/5/2023) - Capacity: 18 |  |  | Sprint 14 (2/6/2023 - 2/12/2023) - Capacity: 24 |  |  | Sprint 15 (2/13/2023 - 2/19/2023) - Capacity: 12 |  | Sprint 16 (2/20/2023 - 2/26/2023) - Capacity: 48 |  | Sprint 17 (2/27/2023 - 3/5/2023) - Capacity: 18 |  |  | Sprint 18 (3/6/2023 - 3/12/2023) - Capacity: 24 |  |  | Sprint 19 (3/13/2023 - 3/19/2023) - Capacity: 12 |  | Sprint 20 (3/20/2023 - 3/19/2023) - Capacity: 48 |  | Sprint 21 (3/27/2023 - 4/2/2023) - Capacity: 18 |  |  | Sprint 22 (4/3/2023 - 4/9/2023) - Capacity: 24 |  |  | Sprint 23 (4/10/2023 - 4/16/2023) - Capacity: 12 |  | Sprint 24 (4/17/2023 - 4/23/2023) - Capacity: 48 |  | Sprint 25 (4/24/2023 - 4/30/2023) - Capacity: 18 |  |  | Sprint 26 (5/1/2023 - 5/7/2023) - Capacity: 24 |  |  | Sprint 27 (5/8/2023 - 5/14/2023) - Capacity: 12 |  | Sprint 28 (5/15/2023 - 5/21/2023) - Capacity | Sprint 28 (5/15/2023 - 5/21/2023) - Capacity
Task # | Task Name
1 | Authentication LLD Success |  | 8hrs
2 | Authentication LLD Failure |  | 8hrs
3 | Authorization LLD Success |  | 8hrs
4 | Authorization LLD Failure |  | 8hrs
5 | Account Recovery LLD Success |  | 8hrs
6 | Account Recovery LLD Failure |  | 8hrs
7 | Authentication Create Interfaces |  |  |  | 2hrs
8 | Authentication Create Tests |  |  |  |  | 4hrs
9 | Authorization Create Interfaces |  |  |  | 2hrs
10 | Authorization Create Tests |  |  |  |  | 4hrs
11 | Account Recovery Create Interfaces |  |  |  | 2hrs
12 | Account Recovery Create Tests |  |  |  |  | 4hrs
13 | BoM | [7 empty] | 8hrs
14 | Authentication Code Design | [6 empty] | 4hrs
15 | Authentication Unit Testing and Adjustments | [7 empty] | 4hrs
16 | Authorization Code Design | [6 empty] | 4hrs
17 | Authorization Unit Testing and Adjustments | [7 empty] | 4hrs
18 | Account Recovery Code Design | [6 empty] | 4hrs
19 | Account Recovery Unit Testing and Adjustments | [7 empty] | 4hrs
20 | Authentication Integration and Integration Testing | [10 empty] | 4hrs
21 | Authorization Integration and Integration Testing | [10 empty] | 4hrs
22 | Account Recovery Integration and Integration Testing | [10 empty] | 4hrs
23 | Registration Code Redesign | [9 empty] | 2hrs
24 | Registration Unit Tests and Adjustments | [10 empty] | 2hrs
25 | Registration Code Integrations and Integration Testing | [11 empty] | 4hrs
26 | Registration LLD Success | [10 empty] | 4hrs
27 | Registration LLD Failure | [10 empty] | 4hrs
28 | User Types LLD Success | [13 empty] | 8hrs
29 | User Types LLD Failure | [13 empty] | 8hrs
30 | User Management LLD Success | [13 empty] | 8hrs
31 | User Management LLD Failure | [13 empty] | 8hrs
32 | Sign In/Out Recovery LLD Success | [13 empty] | 8hrs
33 | Sign In/Out Recovery LLD Failure | [13 empty] | 8hrs
34 | User Types Create Interfaces | [15 empty] | 2hrs
35 | User Types Create Tests | [16 empty] | 4hrs
36 | User Management Create Interfaces | [15 empty] | 2hrs
37 | User Management Create Tests | [16 empty] | 4hrs
38 | Sing In/Out Create Interfaces | [15 empty] | 2hrs
39 | Sing In/Out Create Tests | [16 empty] | 4hrs
40 | User Types Code Design | [18 empty] | 4hrs
41 | User Types Unit Testing and Adjustments | [19 empty] | 4hrs
42 | User Management Code Design | [18 empty] | 4hrs
43 | User Management Unit Testing and Adjustments | [19 empty] | 4hrs
44 | Sign In/Out Code Design | [18 empty] | 4hrs
45 | Sign In/Out Unit Testing and Adjustments | [19 empty] | 4hrs
46 | User Types Integration and Integration Testing | [21 empty] | 4hrs
47 | User Management Integration and Integration Testing | [21 empty] | 4hrs
48 | Sign In/Out Integration and Integration Testing | [21 empty] | 4hrs
49 | Litter Map LLD Success | [23 empty] | 8hrs
50 | Litter Map LLD Failure | [23 empty] | 8hrs
51 | Pinning LLD Success | [23 empty] | 8hrs
52 | Pinning LLD Failure | [23 empty] | 8hrs
53 | Alerts LLD Success | [23 empty] | 8hrs
54 | Alerts LLD Failure | [23 empty] | 8hrs
55 | Litter Map Create Interfaces | [25 empty] | 2hrs
56 | Litter Map Create Tests | [26 empty] | 4hrs
57 | Pinning Create Interfaces | [25 empty] | 2hrs
58 | Pinning Create Tests | [26 empty] | 4hrs
59 | Alerts Create Interfaces | [25 empty] | 2hrs
60 | Alerts Create Tests | [26 empty] | 4hrs
61 | Litter Map Code Design | [28 empty] | 4hrs
62 | Litter Map Unit Testing and Adjustments | [29 empty] | 4hrs
63 | Pinning Code Design | [28 empty] | 4hrs
64 | Pinning Unit Testing and Adjustments | [29 empty] | 4hrs
65 | Alerts Code Design | [28 empty] | 4hrs
66 | Alerts Unit Testing and Adjustments | [29 empty] | 4hrs
67 | Litter Map Integration and Integration Testing | [31 empty] | 4hrs
68 | Pinning Integration and Integration Testing | [31 empty] | 4hrs
69 | Alerts Integration and Integration Testing | [31 empty] | 4hrs
70 | Reputation LLD Success | [33 empty] | 8hrs
71 | Reputation LLD Failure | [33 empty] | 8hrs
72 | Events LLD Success | [33 empty] | 8hrs
73 | Events LLD Failure | [33 empty] | 8hrs
74 | Picture Upload LLD Success | [33 empty] | 8hrs
75 | Picture Upload LLD Failure | [33 empty] | 8hrs
76 | Reputation Create Interfaces | [35 empty] | 2hrs
77 | Reputation Create Tests | [36 empty] | 4hrs
78 | Events Create Interfaces | [35 empty] | 2hrs
79 | Events Create Tests | [36 empty] | 4hrs
80 | Picture Upload Create Interfaces | [35 empty] | 2hrs
81 | Picture Upload Create Tests | [36 empty] | 4hrs
82 | Reputation Code Design | [38 empty] | 4hrs
83 | Reputation Unit Testing and Adjustments | [39 empty] | 4hrs
84 | Events Code Design | [38 empty] | 4hrs
85 | Events Unit Testing and Adjustments | [39 empty] | 4hrs
86 | Picture Upload Code Design | [38 empty] | 4hrs
87 | Picture Upload Unit Testing and Adjustments | [39 empty] | 4hrs
88 | Reputation Integration and Integration Testing | [41 empty] | 4hrs
89 | Events Integration and Integration Testing | [41 empty] | 4hrs
90 | Picture Upload Integration and Integration Testing | [41 empty] | 4hrs
91 | User Services LLD Success | [43 empty] | 8hrs
92 | User Services LLD Failure | [43 empty] | 8hrs
93 | Analytics LLD Success | [43 empty] | 8hrs
94 | Analytics LLD Failure | [43 empty] | 8hrs
95 | UI LLD Success | [43 empty] | 8hrs
96 | UI LLD Failure | [43 empty] | 8hrs
97 | User Services Create Interfaces | [45 empty] | 2hrs
98 | User Services Create Tests | [46 empty] | 4hrs
99 | Analytics Create Interfaces | [45 empty] | 2hrs
100 | Analytics Create Tests | [46 empty] | 4hrs
101 | UI Create Interfaces | [45 empty] | 2hrs
102 | UI Create Tests | [46 empty] | 4hrs
103 | User Services Code Design | [48 empty] | 4hrs
104 | User Services Unit Testing and Adjustments | [49 empty] | 4hrs
105 | Analytics Code Design | [48 empty] | 4hrs
106 | Analytics Unit Testing and Adjustments | [49 empty] | 4hrs
107 | UI Code Design | [48 empty] | 4hrs
108 | UI Unit Testing and Adjustments | [49 empty] | 4hrs
109 | User Services Integration and Integration Testing | [51 empty] | 4hrs
110 | Analytics Integration and Integration Testing | [51 empty] | 4hrs
111 | UI Integration and Integration Testing | [51 empty] | 4hrs

## v2
|  | Semester 1 |  |  |  | Semester 2
| 4 Hour per column | Sprint 8 (11/14/2022 - 11/20/2022) - Capacity: 32 hrs | Sprint 9 (11/21/2022 - 11/27/2022) - Capacity: 40 hrs | Sprint 10 (11/28/2022 - 12/4/2022) - Capacity: 40 | Sprint 11 (12/5/2022 - 12/11/2022) - Capacity: 16 | Sprint 12 (1/23/2023 - 1/29/2023) - Capacity: 8 | Sprint 13 (1/30/2023 - 2/5/2023) - Capacity: 40 | Sprint 14 (2/6/2023 - 2/12/2023) - Capacity: 40 | Sprint 15 (2/13/2023 - 2/19/2023) - Capacity: 40 | Sprint 16 (2/20/2023 - 2/26/2023) - Capacity: 40 | Sprint 17 (2/27/2023 - 3/5/2023) - Capacity: 40 | Sprint 18 (3/6/2023 - 3/12/2023) - Capacity: 40 | Sprint 19 (3/13/2023 - 3/19/2023) - Capacity: 40 | Sprint 20 (3/20/2023 - 3/19/2023) - Capacity: 40 | Sprint 21 (3/27/2023 - 4/2/2023) - Capacity: 40 | Sprint 22 (4/3/2023 - 4/9/2023) - Capacity: 40 | Sprint 23 (4/10/2023 - 4/16/2023) - Capacity: 40 | Sprint 24 (4/17/2023 - 4/23/2023) - Capacity: 40 | Sprint 25 (4/24/2023 - 4/30/2023) - Capacity: 0 | Sprint 26 (5/1/2023 - 5/7/2023) - Capacity: 0 | Sprint 27 (5/8/2023 - 5/14/2023) - Capacity: 0 | Sprint 28 (5/15/2023 - 5/21/2023) - Capacity: 0 | Sprint 28 (5/15/2023 - 5/21/2023) - Capacity:0
Work Item # | Work Item
1 | Log Out LLD 8hrs
2 | Authentication LLD 8hrs
3 | Authorization LLD 8hrs
4 | Authentication Code 32hrs
5 | Dar Reports
6 | User Types Code 8hrs
7 | Authorization Code 32hrs
8 | Log Out Code 8hrs
9 | Registration Code 8hrs
10 | BoM 8hrs
11 | Account Recovery LLD 8 hrs
12 | Account Recovery Code 32hrs
13 | Account Deletion LLD 8hrs
14 | Account Deletion Code 32hrs
15 | User Management LLD 8hrs
16 | User Management 32hrs
17 | UI LLD 8hrs
18 | UI 32hrs
19 | Analytics LLD 8hrs
20 | Analytics 32hrs
21 | Litter Map LLD 8hrs
22 | Litter Map 32hrs
23 | Pinning LLD 8hrs
24 | Pinning 32hrs
25 | Alerts LLD 8hrs
26 | Alerts 32hrs
27 | Reputation LLD 8hrs
28 | Reputation 32hrs
29 | Events LLD 8hrs
30 | Events 32hrs
31 | Picture Upload LLD 8hrs
32 | Picture Upload 32hrs
33 | User Services LLD 8hrs
34 | User Services 32hrs

## v3
|  | Semester 1 |  |  |  | Semester 2
| 4 Hour per column | Sprint 8 (11/14/2022 - 11/20/2022) - Capacity: 32 hrs | Sprint 9 (11/21/2022 - 11/27/2022) - Capacity: 40 hrs | Sprint 10 (11/28/2022 - 12/4/2022) - Capacity: 40 | Sprint 11 (12/5/2022 - 12/11/2022) - Capacity: 16
Work Item # | Work Item
1 | Log Out LLD 8hrs
2 | Authentication LLD 8hrs
3 | Authorization LLD 8hrs
4 | Authentication Code 32hrs
5 | Dar Reports
6 | User Types Code 8hrs
7 | Authorization Code 32hrs
8 | Log Out Code 8hrs
9 | Registration Code 8hrs
10 | BoM 8hrs
|  | Sprint 12 (1/23/2023 - 1/29/2023) - Capacity: 8 | Sprint 13 (1/30/2023 - 2/5/2023) - Capacity: 40 | Sprint 14 (2/6/2023 - 2/12/2023) - Capacity: 40 | Sprint 15 (2/13/2023 - 2/19/2023) - Capacity: 40
Work Item # | Work Item
11 | Account Recovery LLD 8 hrs
12 | Account Recovery Code 32hrs
13 | Account Deletion LLD 8hrs
14 | Account Deletion Code 32hrs
15 | User Management LLD 8hrs
16 | User Management 32hrs
17 | UI LLD 8hrs
|  | Sprint 16 (2/20/2023 - 2/26/2023) - Capacity: 40 | Sprint 17 (2/27/2023 - 3/5/2023) - Capacity: 40 | Sprint 18 (3/6/2023 - 3/12/2023) - Capacity: 40 | Sprint 19 (3/13/2023 - 3/19/2023) - Capacity: 40
Work Item # | Work Item
18 | UI 32hrs
19 | Analytics LLD 8hrs
20 | Analytics 32hrs
21 | Litter Map LLD 8hrs
22 | Litter Map 32hrs
23 | Pinning LLD 8hrs
24 | Pinning 32hrs
25 | Alerts LLD 8hrs
|  | Sprint 20 (3/20/2023 - 3/19/2023) - Capacity: 40 | Sprint 21 (3/27/2023 - 4/2/2023) - Capacity: 40 | Sprint 22 (4/3/2023 - 4/9/2023) - Capacity: 40 | Sprint 23 (4/10/2023 - 4/16/2023) - Capacity: 40
Work Item # | Work Item
26 | Alerts 32hrs
27 | Reputation LLD 8hrs
28 | Reputation 32hrs
29 | Events LLD 8hrs
30 | Events 32hrs
31 | Picture Upload LLD 8hrs
32 | Picture Upload 32hrs
33 | User Services LLD 8hrs
|  | Sprint 24 (4/17/2023 - 4/23/2023) - Capacity: 40 | Sprint 25 (4/24/2023 - 4/30/2023) - Capacity: 0 | Sprint 26 (5/1/2023 - 5/7/2023) - Capacity: 0 | Sprint 27 (5/8/2023 - 5/14/2023) - Capacity: 0
Work Item # | Work Item
34 | User Services 32hrs
|  | Sprint 28 (5/15/2023 - 5/21/2023) - Capacity: 0 | Sprint 28 (5/15/2023 - 5/21/2023) - Capacity:0
Work Item # | Work Item

## roadmap
|  | Semester 1 |  |  |  |  | Every column is a week |  | November |  | December | January |  | February |  | March |  | April |  | May
| 4 Hour per column | Sprint 8 (11/14/2022 - 11/20/2022) - Capacity: 32 hrs | Sprint 9 (11/21/2022 - 11/27/2022) - Capacity: 40 hrs | Sprint 10 (11/28/2022 - 12/4/2022) - Capacity: 40 | Sprint 11 (12/5/2022 - 12/11/2022) - Capacity: 16 | Semester # | Milestone # | Milstone Item
Work Item # | Work Item |  |  |  |  | 1 | 3 | Account Security Part 1 |  | Milestone 3 (11/14/22 - 12/11/22)
1 | Log Out LLD 8hrs | [5 empty] | Includes: Authentication, Authorization, Log out, User types, BoM
2 | Authentication LLD 8hrs
3 | Authorization LLD 8hrs |  |  |  |  | 2 | 4 | Account Security Part 2 |  |  |  |  | Milestone 4 (1/23/23 - 2/19/23)
Includes: Account Recovery, Account Deletion, User Management
4 | Authentication Code 32hrs
5 | Dar Reports | [5 empty] | 5 | UI | [6 empty] | Milestone 5 (2/20/23 - 3/19/23)
Includes: UI, Litter Map, Analytics
6 | User Types Code 8hrs
7 | Authorization Code 32hrs | [5 empty] | 6 | App Features Part 1 | [8 empty] | Milestone 6 (3/20/23 - 4/16/23)
Includes: Pinning, Alerts, Reputation
8 | Log Out Code 8hrs
9 | Registration Code 8hrs | [5 empty] | 7 | App Features Part 2 | [10 empty] | Milestone 6 (4/17/23 - 4/23/23)
10 | BoM 8hrs | [5 empty] | Includes: Events, Picture Upload, User Service
|  | Sprint 12 (1/23/2023 - 1/29/2023) - Capacity: 8 | Sprint 13 (1/30/2023 - 2/5/2023) - Capacity: 40 | Sprint 14 (2/6/2023 - 2/12/2023) - Capacity: 40 | Sprint 15 (2/13/2023 - 2/19/2023) - Capacity: 40
Work Item # | Work Item
11 | Account Recovery LLD 8 hrs
12 | Account Recovery Code 32hrs
13 | Account Deletion LLD 8hrs
14 | Account Deletion Code 32hrs
15 | User Management LLD 8hrs
16 | User Management 32hrs
17 | UI LLD 8hrs
|  | Sprint 16 (2/20/2023 - 2/26/2023) - Capacity: 40 | Sprint 17 (2/27/2023 - 3/5/2023) - Capacity: 40 | Sprint 18 (3/6/2023 - 3/12/2023) - Capacity: 40 | Sprint 19 (3/13/2023 - 3/19/2023) - Capacity: 40
Work Item # | Work Item
18 | UI 32hrs
19 | Litter Map LLD 8hrs
20 | Litter Map 32hrs
21 | Analytics LLD 8hrs
22 | Analytics 32hrs
23 | Pinning LLD 8hrs
24 | Pinning 32hrs
25 | Alerts LLD 8hrs
|  | Sprint 20 (3/20/2023 - 3/19/2023) - Capacity: 40 | Sprint 21 (3/27/2023 - 4/2/2023) - Capacity: 40 | Sprint 22 (4/3/2023 - 4/9/2023) - Capacity: 40 | Sprint 23 (4/10/2023 - 4/16/2023) - Capacity: 40
Work Item # | Work Item
26 | Alerts 32hrs
27 | Reputation LLD 8hrs
28 | Reputation 32hrs
29 | Events LLD 8hrs
30 | Events 32hrs
31 | Picture Upload LLD 8hrs
32 | Picture Upload 32hrs
33 | User Services LLD 8hrs
|  | Sprint 24 (4/17/2023 - 4/23/2023) - Capacity: 40 | Sprint 25 (4/24/2023 - 4/30/2023) - Capacity: 0 | Sprint 26 (5/1/2023 - 5/7/2023) - Capacity: 0 | Sprint 27 (5/8/2023 - 5/14/2023) - Capacity: 0
Work Item # | Work Item
34 | User Services 32hrs
|  | Sprint 28 (5/15/2023 - 5/21/2023) - Capacity: 0 | Sprint 28 (5/15/2023 - 5/21/2023) - Capacity:0
Work Item # | Work Item